## Sheet1
Priority | Task ID | Task | Dependencies | Status | Time Spent(days) | Owner
High | 5 | Create Class Diagrams | Task ID: 1 | In Progress | 21 | Team | % Done | Total | # Done
High | 11 | Player Heal | Task ID: 6 | In Progress | 1 | Patrick | 54.55% | 22 | 12
High | 1 | Define rules and dynamics of the game | None | Done | 7 | Team
High | 2 | Create User Stories | Task ID: 1 | Done | 1 | Chet
High | 3 | Create Use Case Diagram | Task ID: 1 | Done | 1 | Max
High | 4 | Create Use Case Scenarios | Task ID: 1 | Done | 1 | Samantha
High | 6 | Implement Start Game | Task ID: 5 | Done | 2 | Max
High | 9 | Player Fight Monster | Task ID: 6, 10 | Done | 14 | James/Samantha
High | 10 | Player and Monster Deal Damage | Task ID: 6 | Done | 2 | Patrick/Chet
Medium | 8 | Player Record Score | Task ID: 6, 9, 10 | In Progress | 1 | Max
Medium | 16 | Player View Scores | Task ID: 8 | In Progress | 4 | Max
Medium | 17 | System Output scores to a file | Task ID: 8 | In Progress | 14 | Max
Medium | 18 | System input previous high scores to the game | Task ID: 17 | In Progress | TBD | Max
Medium | 7 | Implement End Game | Task ID: 5 | Done | 2 | Max
Medium | 12 | Ability to run away from enemy | Task ID: 6 | Done | 2 | Patrick/Chet
Medium | 13 | Option to flee | Task ID: 6 | Done | 2 | James/Samantha
Medium | 14 | Option to fight | Task ID: 6 | Done | 2 | James/Samantha
Medium | 15 | Chance to miss | Task ID: 9 | Done | 1 | Patrick/Chet
Low | 19 | System reset Scores | Task ID: 8, 17 | Not Started | TBD | TBD
Low | 20 | Option to play again | Task ID: 7 | Not Started | TBD | TBD
Low | 21 | Admin login | Task ID: 5 | Not Started | TBD | TBD
Reach | 22 | Add Sound to Game | Task ID: All other tasks | Not Started | TBD | TBD
N/A |  | GUI |  | Dropped | TBD | TBD